## Sheet1
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Sprint #
1 | Registration | As a user | I would like to be able to register a new account | so that I can login. | 4 | 1
2 | Login | As a user | I would to be able to login | so that I can access the features of the website. | 0 | 1
3 | Logout | As a user | I would like to be able to logout | so that I can protect data that may be vital to me or my company. | 0 | 1
4 | Toggle Feature | As a Laptop Manager | I would like to be able to switch between a table view and a card view | so that I can easily find what I am looking for and ensure that the information and image for the laptop is correct. | 4 | 1
5 | Laptop Management Search | As a Laptop Manager | I would like to be able to search for laptops | so that I can quickly find a laptop that needs to be edited or deleted. | 1 | 1
6 | Modal Create Form | As a Laptop Manger | I would like to be able to click a button that loads a create form | so that I can create a laptop entry in the catalog. | 8 | 2
7 | Modal Edit Form | As a Laptop Manger | I would like to be able to click a button that loads an edit form | so that I can quickly edit a laptop entry. | 8 | 2
8 | Laptop Record Delete | As a Laptop Manger | I would like to be able to click a delete button | so that I can delete a laptop entry. | 4 | 2
9 | Management Laptop Details Page | As a Laptop Manager | I would like to be able to click a details button | so that I can navigate to a page with the full details and full description for a laptop entry. | 2 | 3
10 | Search Results Persistence | As a Laptop Manager | I would like to be able to see the same search results while switching between table and card view | that I can readily find the information I am looking for. | 1 | 3
11 | Manager Registration | As a Manager | I would like to be able to register a new user | so that I can get an employee started. | 1 | 4
12 | Role Management | As a Manager | I would like to be able to create or delete user roles | so that I can add roles for new pages that require authorization for a particular role or remove roles that were only needed for pages that have been removed from the web application. | 4 | 5
13 | Users Role Management | As a Manager | I would like to be able to assign or unassign roles for a user | so that I can manage who has access to particular features of the site. | 4 | 5
14 | User Role Search | As a Manager | I would like to be able to search for users | so that I can quickly find a particular user. | 1 | 5
15 | Retailer REST API | As a retailer | I would like to be able to consume a REST API | so that I can display the manufacturers data on my website. | 2 | 6
16 | Shopping Searh | As a Customer | I would like to be able search for a particular laptop | so that I can find a laptop of interest. | 1 | 7
17 | Shopping Details Page | As a Customer | I would like to be able to click a button that navigates to a full details page of a laptop entry | so that I can learn more about a particular laptop. | 1 | 7
18 | Products Page Add Cart | As a Customer | I would like to be able to add an item to the cart from the products page | so that I can add more than one item to the cart. | 1 | 7
19 | Cart Page | As a Customer | I would like to see the items in my cart | so that I can know what I am purchasing. | 3 | 8
20 | Cart Page Item Management | As a Customer | I would like to be able to add or remove items in the cart | so that I can manage what I am purchasing without having to navigate to a previous page. | 1 | 8
21 | Checkout | As a Customer | I would like to be able to checkout | so that I can complete my order | 8 | 9
22 | [5 empty] | 9
23 |  |  |  |  | 1 | 9
|  |  |  | Total Estimated Hours: | 60
Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Anticipated Day of Delivery
60 | 58.5714 | 57.1429 | 55.7143 | 54.2857 | 52.8571 | 51.4286 | 50 | 48.5714 | 47.1429 | 45.7143 | 44.2857 | 42.8571 | 41.4286 | 40 | 38.5714 | 37.1429 | 35.7143 | 34.2857 | 32.8571 | 31.4286 | 30 | 28.5714 | 27.1429 | 25.7143 | 24.2857 | 22.8571 | 21.4286 | 20 | 18.5714 | 17.1429 | 15.7143 | 14.2857 | 12.8571 | 11.4286 | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0
Week One
Project:
Sprint # | 1
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 1 | As an app owner, I would like to display a title page so that I can establish the identity of my game. | build view of the title page | John | 2
| 2 | As an app user, I would like to navigate to the login or registration page so that I can login or register as a player. | build navigation controllers | Eric | 1
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint # | 2
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 3 | As an app user, I would like to register myself as a user so that I can login and play the game. | build view | John | 6
|  |  | build model | Eric | 6
| 4 | As an app user, I would like to navigate to the title page so that I can navigate to the login page if I remember my credentials. | build controller | John | 1
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint # | 3
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 5 | As an app user, I would like to see why I can't register so that I can correct my registration information. | rebuild controller | Eric | 6
|  |  | build view for user validation | John | 6
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint # | 4
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 6 | As an app user, I would like to login so that I can play the game | build view | John | 4
|  |  | validate user credentials against database | Eric | 3
|  |  | build controller to navigate to game | John | 1
| 7 | As an app user, I would like to see if my registration was a success so that I can confidently login with my new user details | rebuild controller | John | 1
|  |  | build the view | Eric | 1
| 8 | As an app user, I would like to navigate to the registration page so that I can register my user | build view | John | 1
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint # | 5
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 5 | As an app user, I would like to see the reason I can't login so that I can correct my login information | rebuild controller | John | 6
|  |  | build view for user validation | Eric | 6
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 60 | 60 | 60 | 60 | 60 | 60 | 60
Week Two
Sprint #6
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
| 10 | As an app user I would like to have a game board that responds to input so that I can play the game. | Create game board grid | Eric | 4
|  |  | Make the grid responsive to click events | John | 4 |  | 3 | 3 | 4 | 3 | 4
|  |  | Create a layer for game logic | Eric | 4
|  |  | Provide basic game functionality | John | 4
|  |  | Make image resources available and scaled properly | Eric | 2
|  |  | Ensure that the login redirects to the game board | John | 2
[6 empty] | 0 | 3 | 3 | 4 | 3 | 4 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 3 | 3 | 4 | 3 | 4 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 60 | 60 | 57 | 54 | 50 | 47 | 43
Week Three
Sprint #7
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
| 11 | As an app user I would like to see a losing screen so that I can know when I have lost. | Create a losing message to be displayed to the user when the game is lost. Design the game board to appear as though the player has lost. | John | 5
|  |  | Ensure that the logic leading to a losing condition is valid and that the application performs as expected. | Eric/John | 5 |  |  | 4 | 3 | 5 | 3
| 12 | As an app user I would like to see a winning screen so that I can know when I have won. | Create a winning message to be displayed to the user when the game is won. Design the game board to appear as though the player has won. | Eric/John | 5
|  |  | Ensure that the logic leading to a winning condition is valid and that the application performs as expected. | John | 5
| 13 | As an app owner I would like to have pages use ajax and partial pages so that I can reduce full page reloads and demands on my server and to the client | Create a partial view to be returned upon left click. Find a way to pass the data required to create the partial view to the partial view. | John | 3
|  |  | Determine how to disable default left click and prevent left click ajax calls when a cell is flagged. | Eric/John | 3
| 14 | As an app owner I would like to have the game rules as a business service so that I can abstract the game logic from the front end developers I have hired. | Ensure that all of the business logic is in a separate class. | Eric/John | 3
|  |  | Get rid of ViewBag and put everything required in the service. Find a way to use the business service to create the view without redundancy. | John | 3
| 15 | As an app user I would like to flag cells so that I can keep from clicking a cell that I have determined to be a bomb. | Create a partial view that can be returned to jQuery and be inserted into the flex-grid. | Eric/John | 5
|  |  | Enable right click through the use of jQuery. Design the flags to fit the full height and width of the button. | John | 5
[6 empty] | 0 | 0 | 4 | 3 | 5 | 3 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 0 | 4 | 3 | 5 | 3 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 43 | 43 | 43 | 39 | 36 | 31 | 28
Week Four
Sprint #8
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
| 16 | As an app user I would like to save the game so that I could finish the game later. | Create game DAO and database for accessing saved game documents. Update site.js and the controller to asynchronously call functions like save, delete and show all games. Determine how to serialize, save and load a game. | John | 10 |  | 3 | 3 | 2 | 1
|  |  | Find a way to add links dynamically to the menu so that they are only being loaded once logged in. Determine how a partial view can be used to display a list of saved games. Test and debug the saving, delete and load functions to ensure that the game is ready to hand over to the client. | Eric | 10
| 17 | As an app owner I would like to offer saved game data as a REST service so that I can see all saved games, the state of one game and delete a game if I wish. | Create a REST API and use the game DAO to return an appropriate response. Ensure that the format of the response returned can be handled by the browser. The REST API must be able to show one games save data, delete one games data and show all games. Use route "/api/showSavedGames/?" and "/api/deleteOneGame" | Eric | 10
|  |  | Use postman and the browser to test the REST API. Debug any other part that may pertain to the REST API such as the game DAO. Work on any documents associated with the REST API and game at this stage. | John | 10
[6 empty] | 0 | 3 | 3 | 2 | 1 | 0 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 3 | 3 | 2 | 1 | 0 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 28 | 28 | 25 | 22 | 20 | 19 | 19
Week Five
Sprint #9
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
| 18 | As an app owner I would like to leverage dependency injection so that I can seemlessly switch data storage solutions. | Inject the DAO into the Minesweeper application. | Eric | 6
|  |  | Create a DAO that utilizes another data source. | John | 6
| 19 | As an app owner I would like to leverage HTTP Request filter so that I can provide page security. | Create a request filter and use it to uphold the security of the application. | John | 6
|  |  | Test and debug the request filter to ensure that pages that are only supposed to be accessible through logging in are protected when not logged in. | Eric | 6
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 19 | 19 | 19 | 19 | 19 | 19 | 19
| User Story Id | User Story | Task | Assigned To | Estimate (hours) | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
| 18 | As an app owner I would like to leverage dependency injection so that I can seemlessly switch data storage solutions. | Inject the DAO into the Minesweeper application. | Eric | 6
|  |  | Create a DAO that utilizes another data source. | John | 6 |  | 4 | 4 | 3 | 3 | 3
| 19 | As an app owner I would like to leverage HTTP Request filter so that I can provide page security. | Create a request filter and use it to uphold the security of the application. | John | 6
|  |  | Test and debug the request filter to ensure that pages that are only supposed to be accessible through logging in are protected when not logged in. | Eric | 6
[6 empty] | 0 | 4 | 4 | 3 | 3 | 3 | 0
[5 empty] | Total Hours Burned for All Sprints: | 0 | 4 | 4 | 3 | 3 | 3 | 0
[5 empty] | Estimated Hours of Work Remaining at Beginning of Day | 19 | 19 | 15 | 11 | 8 | 5 | 2